## Project Estimate Phase1
Total Hours Estimate |  | 2405
Total Material Estimate |  | 171.5
Total Hours Actual |  | 7620
Total Material Actual |  | 4
Task | Description | Order | Price Estimate | Price Actual | Hours Estimate | Material Estimate | Hours Actual | Material Actual | Blocked by | Tools Needed | Supplies Needed | alley notes
Foundation | Support main joist under french door, lift up house from there, check for level, re-attach all flooring support, add reinforcement. We have several 16tft 2x6 floor joists. Use these for additional support. Use 2-3 jacks to lift foundation | 0 | 0 | 0 | 12 | 200 | 4 | 0 |  | Bottle jacks, cinderblocks | 2X6 24 ft, cinderblocks | DONE!
small bedrooms walls | Panel small bedroom walls with same paneling as the living room. All material should be cleaned out | 10 |  | 750 | 8 | 150 |  |  |  | skill saw, jig saw, hammer | 9 sheets of paneling, paneling nails, liquid nail | jeff is working on this
Paint Master | Master walls need to be painted ironwood wall color | 11 |  | 500 | 4 | 50 |  |  |  | paint, tape, rollers, brushes
Floor | Master bath, small bath, and small bedroom need to be finished. Transition strip in bedroom, seamless floor to bathroom. | 12 |  | 0 | 8 | 600 |  |  |  | Flooring tools, knee pads, cutter | Flooring
Trim | Base board, door & window casing, chair rail, corners, ceiling, primer, paint. Making a bunch of the wood out of 2x4s with table saw and planar | 13 |  | 2500 | 32 | 800 |  |  |  | compound saw, rollers, brushes, nailer, sander | finish nails, primer, enamel
Toilets | Install toilets, move supply line to correct spot. | 14 | 50 |  | 4 | 400 |  |  | Floors and trim need to be finished behind toilet first | wrenches | toilet, wax-ring, caulk
Install pine shiplap/trim | Master bathroom needs a few more pieces of shiplap up to door. Then outside corner trim there and in living room. | 15 |  | 0 - Done with trim | 2 | 80 |  |  |  | saw, nailer | finish nails
Paint pine trim | Pine shiplap needs to be painted and sanded until its finish is smooth and similar in look to original pine shiplap (in living room) (also pine corner trim) | 16 |  | 0 - Done with trim | 8 | 60 |  |  | Pine corner trim needs to be installed | enamel brushes/roller, sander | clear spar urethane enamel
Fix living room window | Living room window glass broke but the frame is still good. Replace glass or get new window and install | 17 |  | 60 | 1 | 200 |  |  |  | drill | screws, foam insulation?
Paint ceiling | Living room addition ceiling looks like it needs paint. Paint it white. | 18 | 150 |  | 3 | 25 |  |  |  | drop cloth, rollers, brush, tape | white ceiling paint
Install washer dryer | Clean up washer dryer, install and test. Confirm both in good working condition | 20 | 40 |  | 2 | 25 |  |  | Utiltiy room needs to be trimed frist | wrenches | supply hose, exhaust hose
Install bathroom sink and faucet | 2 drolp in sinks and 2 moen faucets need to be installed in both bathrooms | 22 |  | 50 | 5 | 200 |  |  |  | wrenches, plumbing tape
Install Dishwasher | Dishwasher is too tall with flooring under it. Cut out counter to fit dishwasher. Ideally add a designated outlet under the dishwasher instead of romex sticking out of the floor | 24 |  | 0 - Part of the 750 bedroom to jeff | 2 | 20 |  |  |  | Jig Saw/ Sawzall | Outlet
Shower heads | Install shower riser and new shower heads in both bathrooms | 26 | 35 |  | 1 | 120 |  |  |  | Plumbing tape, wrench
Hot tub top | Top of hottub needs to be replaced | 30 | 550 |  | 3 | 400 | [5 empty] | low- free on facebook
R panel insulation on roof | Roof cap needs insulation to block water. Install across both sides where missing | 31 | 100 |  | 2 | 100
Air handler finish | Need to create a register and filter holder for air handler. The bottom of the air handler should be a removable access hatch that is closed off and trimmed. The top should have a register that opens to a 20x25 4 inch air filter for replacing. | 32 | 150 |  | 8 | 120
Starlink internet wires | Starlink intenet wires need to be routed through wall correctly | 34 | 40 |  | 2 | 10
Screw on septic caps | Septic caps come loose when hit or moved. Screw them on for safety | 36 | 10 |  | 0.5 | 0
Fix bootleg gate | Gate to backyard is nonsense. Build with decent wood so its usable or replace all together | 38 | 60 |  | 4 | 200
Move T posts | T posts need to be moved away from main property and stored somwhere | 40 | 20 |  | 3 | 0
Support 4x4 porch posts | Look for wobbly posts and attach with deck screws and black L brackets. | 50 | 100 |  | 3 | 40
Install front storm door | Storm door missing from front but sitting out. Install it. | 52 | 50 |  | 3 | 0
Patio electrical | There should be ceiling fans and lights on the back porch. Need to correctly run electrical for this | 56 | 400 |  | 8 | 500 | [5 empty] | very low- might not do
Kitchen Cabinet Paint | Repair any loose kitchen cabinets with wood glue and finish nails/screws. Paint white. Try to make them look as nice as possible. | 70 - Consider new cabinets | 350 |  | 6 | 120 | [5 empty] | don’t need to paint
Clean up work site | Clean all work mess and put all trash, supplies, furniture, etc. where it is supposed to be | 80 | 100 |  | 12 | 0 |  |  | Job needs to be finihsd
Clean out carport | Carport needs to be cleared out for parking. There should be nothing stored under there | 81 | 100 |  | 3 | 0
Pickup flagstones | All flagstones should be gather onto pallets and moved to back of property | 82 | 100 |  | 6 | 0
Furnish house | Entire house will need to be furnished well. Beds 2x, nightstands, dressers, couches, table, chairs, etc. | 90 |  |  | 16 | 3200 |  |  | Trim should be done first

## Kengs Landing Phase 2
Task | Description | Labor Estimated | Material Cost Estimated | Blocked by
Install front storm door | Storm door missing from front but sitting out. Install it. | 3 | 0
hot tub electrical | I want to install as much breaker amperage and wires as is possible on the little subpanel by the Hottub. There is currently a 60amp breaker. I think it may be possible to do another 30 amps. So maybe two 15 amp circuits. The goal is to be able to install plugs 2-4 and maybe two 3-way switches. I need to be able to turn on light under the hottub. Possibly plug in TV's or fans in the future. Would also like at least 1 plug in receptacle. | 400 |  | Need Gazebo Roof to be installed first
Pond Airator | Install airation pump in a safe place using hot tub electrical. Run air underground across pond | 150 | 200 | Hot tub electrical done
Firepit | Install firepit with 4 chairs. Should include smore setup | 400 | 400
Gazebo Roof | Install roof over gazebo | 600 | 400

## Jacob
Task | Order | Description | Price
Patch and paint walls | 11 | Master walls need to be painted cottage white color, as well as both bathroom since these rooms have drywall. Need to make sure all drywall is patched and pretty. Also paint behind toilets while toilets are removed.
Trim | 13 | Baseboards, door & window casing, chair rail, corners, ceiling, primer, paint. Windows Living Room: These are the only windows that differ. They should have an actual window ceil that sticks out 1-2 inches. The flush window seal that is in there now is just toenailed. My suggestion would be to remove it and put a full piece of wood there that sticks out the correct dimentions. Master Bedroom: Drywall does not need celiing or chair rail trim. Maybe caulk ceiling cracks, if ceiling trim is easier, I am fine with that. Focal wall (Pine): Should have Baseboard, corner, and ceiling trim the same as the the rest of the house framing it. Master Bathroom: Trim pine with
Toilets | 14 | Install toilets, this was not done so that trim and paint could be done behind first as agreed.
Install pine shiplap/trim | 15 | Master bathroom needs a few more pieces of shiplap up to door. Then outside corner trim there and in living room.
Paint pine trim | 16 | New pine shiplap in master bedr needs to be painted and sanded until its finish is smooth and similar in look to original pine shiplap. (also pine corner trim if used. We discussed just doing white trim)
Paint ceiling | 18 | Living room addition ceiling looks like it needs paint. Paint it white.
NEW WORK BELOW | 19 | X X X X X X
Paint doors | 20.1 | Doors were not part of the ogininal paint and trim estimates. I'm assumming that painting the door trim was. But all the actual doors need to be painted as well
Install washer dryer | 21 | Clean up washer dryer, install and test. Confirm both in good working condition
Install bathroom sink and faucet | 22 | 2 drolp in sinks and 2 moen faucets need to be installed in both bathrooms
Shower heads | 26 | Install shower riser and new shower heads in both bathrooms
Air handler finish | 32 | Need to create a register and filter holder for air handler. The bottom of the air handler should be a removable access hatch that is closed off and trimmed. The top should have a register that opens to a 20x25 4 inch air filter for replacing.
Starlink internet wires | 34 | Starlink intenet wires need to be routed through wall correctly
Fix bootleg gate | 38 | Gate to backyard is nonsense. Build with decent wood so its usable or replace all together
Move T posts | 40 | T posts need to be moved away from main property and stored somwhere
Support 4x4 porch posts | 50 | Look for wobbly posts and attach with deck screws and black L brackets.
Install front storm door | 52 | Storm door missing from front but sitting out. Install it.
Patio electrical | 56 | There should be ceiling fans and lights on the back porch. Need to correctly run electrical for this. Would like conduit. Would like additional outlet options for security cameras.
Kitchen Cabinet Paint | 70 | Repair any loose kitchen cabinets with wood glue and finish nails/screws. Paint white. Try to make them look as nice as possible.
Clean up work site | 80 | Clean all work mess and put all trash, supplies, furniture, etc. where it is supposed to be
Clean out carport | 81 | Carport needs to be cleared out for parking. There should be nothing stored under there
Pickup flagstones | 82 | All flagstones should be gather onto pallets and moved to back of property
Furnish house | 90 | Entire house will need to be furnished well. Beds 2x, nightstands, dressers, couches, table, chairs, etc.

## Eric
Task | Description | Order
R panel insulation on roof | Roof cap needs insulation to block water. Install across both sides where missing | 1
Air vents | Install 6 air vents through house | 1
List fridge | Take pictures of fridge and list | 5
List couches | Take pictures of couches and list | 5
Install AC Register | Cut out wall above AC. And install register that accepts 4 inch filter | 10
Furnace relay | Install new furnace relay once it comes in. Make sure furnace turns off | 10
Hot tub top | Top of hottub needs to be replaced | 20
propane heater | pipe dope to gas connection | 1

## Sheet1
Item | Cost | Where | Payment | Notes